## INFORMATION
TEST CASES
PROECT NAME | SWAG LABS
VERSION | 1.O
REPORT AUTHOR | HITESH KANTARITA DHRUV TALSANIYA
REVIEWED BY | *
CREATION DATE | 24/03/2025 TO 26/03/2025
REFERENCE DOC | SWAG LABS - TEST SCENARIO

## LOGIN FOR ALL PAGE
TS_ID | TEST SCENARIOS | TC_ID | TEST CASES | DESCRIPTION | TEST STEPS | EXPECTED RESULT | ACTUAL RESULT | PRIORITY | BUG STATUS | INPUT DATA | COMMENT
TS_01 | LOGIN SUCCESS | TC_01 | RIGHT ID AND RIGHT PASSWORD | VERIFY THAT WITH CORRECT USER ID & CORRECT PASSWORD USER SHOULD SUCCESSFULLY LOGIN | 1. GO TO https://www.saucedemo.com/ 2. CLICK ON FIELD NAME USERNAME 3. FILL CURRENT USERNAME 4. FILL CORRECT PASSWORD 5. CLICK ON LOGIN BUTTON 6. VERIFY THAT USER IS LOGGED IN | LOGIN SUCCESSFULL | DONE |  | NO BUG | DATA : USERNAME: standard_user PASSWORD: secret_sauce (ANY PAGE USERNAME AND PASSWORD)
TS_02 | LOGIN FAIL | TC_02 | RIGHT ID AND WRONG PASSWORD | VERIFY THAT WITH CORRECT USER ID & WRONG PASSWORD USER SHOULD NOT SUCCESSFULLY LOGIN | 1. GO TO https://www.saucedemo.com/ 2. CLICK ON FIELD NAME USERNAME 3. FILL CORRECT USERNAME 4. FILL WRONG PASSWORD 5. CLICK ON LOGIN BUTTON 6. VERIFY THAT USER IS NOT LOGGED IN | USER NOT LOGIN | DONE |  | NO BUG | DATA : USERNAME RIGHT AND PASSWORD WRONG (ANY PAGE USERNAME AND PASSWORD)
|  | TC_03 | WRONG ID AND RIGHT PASSWORD | VERIFY THAT WITH WRONG USER ID & CORRECT PASSWORD USER SHOULD NOT SUCCESSFULLY LOGIN | 1. GO TO https://www.saucedemo.com/ 2. CLICK ON FIELD NAME USERNAME 3. FILL WRONG USERNAME 4. FILL CORRECT PASSWORD 5. CLICK ON LOGIN BUTTON 6. VERIFY THAT USER IS NOT LOGGED IN | USER NOT LOGIN | DONE |  | NO BUG | DATA : USERNAME WRONG AND PASSWORD RIGHT (ANY PAGE USERNAME AND PASSWORD)
|  | TC_04 | WRONG ID AND WRONG PASSWORD | VERIFY THAT WITH WRONG USER ID & WRONG PASSWORD USER SHOULD NOT SUCCESSFULLY LOGIN | 1. GO TO https://www.saucedemo.com/ 2. CLICK ON FIELD NAME USERNAME 3. FILL WRONG USERNAME 4. FILL WRONG PASSWORD 5. CLICK ON LOGIN BUTTON 6. VERIFY THAT USER IS NOT LOGGED IN | USER NOT LOGIN | DONE |  | NO BUG | DATA : USERNAME AND PASSWORD BOTH WRONG (ANY PAGE USERNAME AND PASSWORD)
|  | TC_05 | EMPTY ID AND EMPTY PASSWORD | VERIFY THAT WITH EMPTY USER ID & EMPTY PASSWORD USER SHOULD NOT SUCCESSFULLY LOGIN AND ERROR MESSAGE IS DISPLAY | 1. GO TO https://www.saucedemo.com/ 2. CLICK ON FIELD NAME USERNAME 3. FILL EMPTY USERNAME 4. FILL EMPTY PASSWORD 5. CLICK ON LOGIN BUTTON 6. VERIFY THAT USER IS NOT LOGGED IN | USER NOT LOGIN | DONE |  | NO BUG | DATA : USERNAME AND PASSWORD BOTH EMPTY (ANY PAGE USERNAME AND PASSWORD)
|  | TC_06 | ANYONE FIELD EMPTY AND ANYONE FIELD FILL | VERIFY THAT WITH EMPTY USER ID & FILL PASSWORD USER SHOULD NOT SUCCESSFULLY LOGIN AND ERROR MESSAGE IS DISPLAY | 1. GO TO https://www.saucedemo.com/ 2. CLICK ON FIELD NAME USERNAME 3. FILL EMPTY USERNAME 4. FILL PASSWORD 5. CLICK ON LOGIN BUTTON 6. VERIFY THAT USER IS NOT LOGGED IN | USER NOT LOGIN | DONE |  | NO BUG | DATA : USERNAME AND PASSWORD ANYONE IS EMPTY (ANY PAGE USERNAME AND PASSWORD)

## STANDARD_USER
TS_ID | TEST SCENARIOS | TC_ID | TEST CASES | DESCRIPTION | TEST STEPS | EXPECTED RESULT | ACTUAL RESULT | PRIORITY | BUG STATUS | INPUT DATA | COMMENT
TS_01 | LOGIN SUCCESS | TC_01 | RIGHT ID AND RIGHT PASSWORD | VERIFY THAT WITH CORRECT USER ID & CORRECT PASSWORD USER SHOULD SUCCESSFULLY LOGIN (id : standard_user password : secret_sauce ) | 1. GO TO https://www.saucedemo.com/ 2. CLICK ON FIELD NAME USERNAME 3. FILL CURRENT USERNAME 4. FILL CORRECT PASSWORD 5. CLICK ON LOGIN BUTTON 6. VERIFY THAT USER IS LOGGED IN | USER SHOULD LOGIN SUCESSFULLY. | DONE. |  | NO BUG | DATA : USERNAME: standard_user PASSWORD: secret_sauce | NA
|  | TC_02 | EYE BUTTON WORKING PROPERLY | VERIFY THAT EYE BUTTON WORKING PROPERLY | 1. GO TO https://www.saucedemo.com/ 2. CLICK ON FIELD NAME USERNAME 3. FILL CURRENT USERNAME 4. FILL CORRECT PASSWORD | USER SHOULD VIEW PASSWORD PROPERLY WITH EYE BUTTON. | NOT EYE BUTTON WORK PROPERLY ACROSS BROWSER. | MINOR | RE - TEST | NA | EYE BUTTON SHOWING IN : MICROSOFT EDGE NOT SHOWING IN : CHROME, BRAVE, FIREFOX
TS_02 | REDIRECT WEBSITE | TC_03 | RIGHT ID AND RIGHT PASSWORD CHECK REDIRECT TO STANDARD_USER WEBSITE | VERIFY THAT WITH CORRECT USER ID & CORRECT PASSWORD USER SHOULD SUCCESSFULLY LOGIN AND REDIRECT TO STANDARD_USER WEBSITE (id : standard_user password : secret_sauce ) | 1. GO TO https://www.saucedemo.com/ 2. CLICK ON FIELD NAME USERNAME 3. FILL CURRENT USERNAME 4. FILL CORRECT PASSWORD 5. CLICK ON LOGIN BUTTON 6. VERIFY THAT USER IS LOGGED IN 7. VERIFY REDIRECT WEBSITE IS STANDARD_USER | USER SHOULD REDIRECT TO HOME PAGE SUCESSFULLY. | DONE. |  | NO BUG | DATA : USERNAME: standard_user PASSWORD: secret_sauce | NA
TS_03 | RED BORDER AROUND INPUT FIELD | TC_04 | CHECK RED BORDER IN BOTH FIELD | VERIFY THAT RED BORDER IS SHOWN ONLY ON EMPTY FIELD | 1. GO TO https://www.saucedemo.com/ 2. CLICK ON FIELD NAME USERNAME 3. FILL WRONG USERNAME 4. FILL CORRECT PASSWORD 5. CLICK ON LOGIN BUTTON 6. VERIFY THAT USER IS NOT LOGGED IN | USER SHOULD VIEW A RED BORDER AROUND EMPTY OR INCORRECT FIELDS. | RED BORDER IS NOT DISPLAYED AROUND EMPTY OR INCORRECT FIELDS. | MINOR | RE - TEST | NA | NA
TS_04 | INPUT FIELD IN CART | TC_05 | CHECK THAT INPUT FIELD CONTAIN CHARACTERS | BOTH FIELD ACCEPT CHARACTERS AS A INPUT (FIRST_NAME AND LAST_NAME) | 1. GO TO https://www.saucedemo.com/ 2. LOGIN INTO PAGE 3. GO TO CART 4. GO TO CHECKOUT 5. ENTER FIRST_NAME AND LAST_NAME | USER SHOULD SUCCESSFULLY WRITE CHARACTERS IN FIRST NAME AND LAST NAME FIELDS. | DONE. |  | NO BUG | FIRST NAME : A TO Z LAST NAME : A TO Z | NA
|  | TC_06 | CHECK THAT INPUT FIELD NOT ACCEPT NUMBERS AND SPECIAL CHAR | CHECK THAT INPUT FIELD NOT ACCEPT NUMBERS AND SPECIAL CHAR (FIRST_NAME AND LAST_NAME) | 1. GO TO https://www.saucedemo.com/ 2. LOGIN INTO PAGE 3. GO TO CART 4. GO TO CHECKOUT 5. ENTER FIRST_NAME AND LAST_NAME | USER SHOULD NOT BE ABLE TO WRITE NUMBERS OR SPECIAL CHARACTERS IN FIRST NAME AND LAST NAME FIELDS. | USER IS ABLE TO WRITE NUMBERS OR SPECIAL CHARACTERS IN FIRST NAME AND LAST NAME FIELDS. | MAJOR | RE - TEST | FIRST NAME : 123456@# LAST NAME : 123456@# | NA
|  | TC_07 | CHECK THAT INPUT FIELD CONTAIN NUMBERS | BOTH FIELD ACCEPT NUMBERS AS A INPUT (ZIP CODE) | 1. GO TO https://www.saucedemo.com/ 2. LOGIN INTO PAGE 3. GO TO CART 4. GO TO CHECKOUT 5. ENTER ZIP CODE | USER SHOULD SUCCESSFULLY ENTER NUMBERS IN ZIP CODE FIELD. | DONE. |  | NO BUG | ZIP CODE : 123-456 | NA
|  | TC_08 | CHECK THAT INPUT FIELD NOT ACCEPT CHARACTER AND SPECIAL CHAR | CHECK THAT INPUT FIELD NOT ACCEPT NUMBERS AND SPECIAL CHAR (ZIP CODE) | 1. GO TO https://www.saucedemo.com/ 2. LOGIN INTO PAGE 3. GO TO CART 4. GO TO CHECKOUT 5. ENTER ZIP CODE | USER SHOULD NOT BE ABLE TO ENTER CHARACTERS OR SPECIAL CHARACTERS IN ZIP CODE FIELD. | USER IS ABLE TO ENTER CHARACTERS OR SPECIAL CHARACTERS IN ZIP CODE FIELD. | MAJOR | RE - TEST | ZIP CODE : ABCD@#$ | NA
TS_05 | ORDER IN CART | TC_09 | VERIFY THAT IF NO PRODUCT THAN DO NOT PROCEED TO ORDER | VERIFY THAT IF CART EMPTY THAN USER UNABLE TO GO FURTHER PROCEDURE | 1. GO TO https://www.saucedemo.com/ 2. LOGIN INTO PAGE 3. GO TO CART 4. GO TO CHECKOUT 5. ENTER ALL DETAILS 6. CLICK TO CHECKOUT | USER SHOULD NOT BE ABLE TO PROCEED TO ORDER WHEN THE CART IS EMPTY. | USER IS ABLE TO PROCEED TO ORDER EVEN WHEN THE CART IS EMPTY. | MAJOR | RE - TEST | NA | NA
|  | TC_10 | VERIFY THAT QUANTITY OF PRODUCT | VERIFY THAT USER CAN INCREASE OR DECREASE THE QUANTITY OF PRODUCT | 1. GO TO https://www.saucedemo.com/ 2. LOGIN INTO PAGE 3. GO TO CART 4. INCREASE OR DECREASE THE PRODUCT QUANTITY | USER SHOULD BE ABLE TO INCREASE OR DECREASE THE QUANTITY OF THE PRODUCT. | USER CANNOT INCREASE OR DECREASE THE QUANTITY OF THE PRODUCT. | MINOR | RE - TEST | NA | NA
|  | TC_11 | VERIFY THAT ENTER BUTTON WORKING IN CHECKOUT | CHECK THAT WHEN USER ENTER ALL DETAILS AND CLICK ENTER THEN ENTER BUTTON WORKING | 1. GO TO https://www.saucedemo.com/ 2. LOGIN INTO PAGE 3. GO TO CART 4. GO TO CHECKOUT 5. ENTER ALL DETAILS 6. CLICK ENTER | USER SHOULD BE ABLE TO LOG IN AFTER FILLING IN ALL DETAILS AND PRESSING THE ENTER BUTTON. | DONE. |  | NO BUG | NA | NA
|  | TC_12 | VERIFY THAT ERROR MESSAGE SHOWN | VERIFY THAT ERROR MESSAGE SHOWN FOR ALL EMPTY FIELDS | 1. GO TO https://www.saucedemo.com/ 2. LOGIN INTO PAGE 3. GO TO CART 4. GO TO CHECKOUT 5. DO NOT ENTER ALL DETAILS 6. CLICK TO CHECKOUT | USER SHOULD VIEW A RED BORDER AROUND EMPTY FIELDS. | DONE. |  | NO BUG | NA | NA
TS_06 | GO BACK BUTTON | TC_13 | VERIFY THAT IF USER GO BACK THAN UNABLE TO IN LOGGED IN PAGE | LOGIN > USER PAGE > LOGIN > USER PAGE, USER CAN NOT DO THIS IF TRY FOR THIS THEN RESTART SESSION | 1. GO TO https://www.saucedemo.com/ 2. LOGIN INTO PAGE 3. GO BACK TO LOGIN PAGE 4. GO TO PREVIOUS PAGE AGAIN | USER SHOULD NOT BE REDIRECTED FROM HOME PAGE TO LOGIN PAGE DIRECTLY WITHOUT SESSION TIMEOUT. | USER IS REDIRECTED FROM HOME PAGE TO LOGIN PAGE WITHOUT SESSION TIMEOUT. | BLOCKER | RE - TEST | NA | NA

## PROBLEM_USER
TS_ID | TEST SCENARIOS | TC_ID | TEST CASES | DESCRIPTION | TEST STEPS | EXPECTED RESULT | ACTUAL RESULT | PRIORITY | STATUS | INPUT DATA | COMMENT
TS_01 | LOGIN SUCCESS | TC_01 | RIGHT ID AND RIGHT PASSWORD | VERIFY THAT WITH CORRECT USER ID & CORRECT PASSWORD USER SHOULD SUCCESSFULLY LOGIN (id : problem_user password : secret_sauce) | 1. GO TO https://www.saucedemo.com/ 2. CLICK ON FIELD NAME USERNAME 3. FILL CORRECT USERNAME 4. FILL CORRECT PASSWORD 5. CLICK ON LOGIN BUTTON 6. VERIFY THAT USER IS LOGGED IN | USER SUCCESSFULLY LOG IN WITH VALID USERNAME AND PASSWORD. | DONE. |  | NO BUG | USERNAME: problem_user PASSWORD: secret_sauce | NA
TS_02 | REDIRECT WEBSITE | TC_02 | RIGHT ID AND RIGHT PASSWORD CHECK REDIRECT TO PROBLEM_USER WEBSITE | VERIFY THAT WITH CORRECT USER ID & CORRECT PASSWORD USER SHOULD SUCCESSFULLY LOGIN AND REDIRECT TO PROBLEM_USER WEBSITE (id : problem_user password : secret_sauce ) | 1. GO TO https://www.saucedemo.com 2. CLICK ON FIELD NAME USERNAME 3. FILL CURRENT USERNAME 4. FILL CORRECT PASSWORD 5. CLICK ON LOGIN BUTTON 6. VERIFY THAT USER IS LOGGED IN 7. VERIFY REDIRECT WEBSITE IS STANDARD_USER https://www.saucedemo.com/inventory.html | USER SHOULD REDIRECT TO HOMEPAGE SUCCESSFULLY. | DONE. |  | NO BUG | USERNAME: problem_user PASSWORD: secret_sauce | NA
TS_03 | RED BORDER AROUND INPUT FIELD | TC_03 | CHECK RED BORDER | VERIFY THAT RED BORDER IS SHOWN ONLY ON EMPTY FIELD | 1. GO TO https://www.saucedemo.com/ 2. CLICK ON FIELD NAME USERNAME 3. FILL WRONG USERNAME 4. FILL CORRECT PASSWORD 5. CLICK ON LOGIN BUTTON 6. VERIFY THAT USER IS NOT LOGGED IN | USER SEES A RED BORDER AROUND EMPTY FIELDS ON THE LOGIN PAGE. | DONE. |  | NO BUG | NA | NA
TS_04 | ADD TO CART | TC_04 | ADD PRODUCT TO CARD | VERIFY THAT ALL PRODUCT SHOULD ADD TO CART SUCCESSFULLY | 1. GO TO https://www.saucedemo.com/ 2. LOGIN TO PAGE 2. CLICK ON ANY PRODUCT ADD TO CART 3. VERIFY PRODUCT IS ADD INTO CART | USER SUCCESSFULLY ADDS ITEM TO CART. | USER SHOULD NOT BE ABLE TO ADD ALL ITEMS TO THE CART . | MAJOR | RE - TEST | NA | USER CAN UNABLE TO ADD SOME PRODUCT IN CART
TS_05 | REMOVE FROM CART | TC_05 | REMOVE PRODUCT | VERIFY THAT ALL PRODUCT SHOULD REMOVE FROM CART SUCCESSFULLY | 1. GO TO https://www.saucedemo.com/ 2. LOGIN TO PAGE 3. CLICK ON ANY PRODUCT ADD TO CART 4. VERIFY PRODUCT IS ADD INTO CART 5. CLICK ON THAT PRODUCT REMOVE BUTTON 6. VERIFY PRODUCT REMOVE FROM CART | USER SUCCESSFULLY REMOVES ITEM FROM CART. | ITEM IS NOT REMOVED FROM CART OR REMOVAL BUTTON DOES NOT WORK. | MAJOR | RE - TEST | NA | SOME PRODUCT IS NOT REMOVE FROM CART PROPERLY
TS_06 | PRODUCT DETAILS | TC_06 | OPEN PRODUCT DETAILS | VERIFY THAT ALL PRODUCT DETAILS SHOULD OPEN SUCCESSFULLY | 1. GO TO https://www.saucedemo.com/ 2. LOGIN TO PAGE 3. CLICK ON ANY PRODUCT NAME OR IMAGE 4. VERIFY PRODUCT DETAILS IS OPEN OR NOT 5. VERIFY PRODUCT DETAILS OPEN SUCCESSFULLY | USER VIEW PRODUCT DETAILS BASED ON THE SELECTED ITEM. | PRODUCT DETAILS NOT FIXED IT IS CHANGE MANY TIME. | MAJOR | RE - TEST | NA | PRODUCT DETAILS NOT DISPLAY PROPERLY & SOME TIME CHANGE DETAILS OF PRODUCT
TS_07 | FILTER OF PRODUCT | TC_07 | FILTER APPLY ON PRODUCT | VERIFY THAT ALL PRODUCT ARRANGE ACCORDING TO PRODUCT FILTER | 1. GO TO https://www.saucedemo.com/ 2. LOGIN TO PAGE 3. CLICK ON FILTER OF PRODUCT 4. VERIFY PRODUCT ARRANGE ACCORDING TO FILTER 5. VERIFY PRODUCT ARRANGE ACCORDING TO FILTER SUCCESSFULLY | PRODUCT FILTER WORKS CORRECTLY WITHOUT ANY ISSUES. | USER CANNOT FILTER PRODUCTS PROPERLY. | MAJOR | RE - TEST | NA | NOT WORKING FILTER OF PRODUCT
TS_08 | CHECKOUT FAIL | TC_08 | VERIFY CHECKOUT BUTTON | VERIFY ALL CHECKOUT FIELD DETAILS WITH PRODUCT ORDER DETAILS | 1. GO TO https://www.saucedemo.com/ 2. LOGIN TO PAGE 3. CLICK ON CHECKOUT ICON 4. VERIFY CHECKOUT BUTTON OPEN SUCCESSFULLY 5. VERIFY PRODUCT IS PRESENT IN CHECKOUT FIELD 6. CLICK ON CHECKOUT BUTTON 7. CHECK PRODUCT PRESENT IN CHECKOUT | CHECKOUT BUTTON SHOULD BE DISABLED OR SHOW AN ERROR WHEN NO PRODUCT IS IN THE CART. | CHECKOUT BUTTON WORKS EVEN WITHOUT ANY PRODUCT IN THE CART. | MAJOR | RE - TEST | NA | CHECKOUT BUTTON WORK WITHOUT ANY PRODUCT
TS_09 | CHECKOUT SUCCESSFULLY | TC_09 | CHECKOUT WITH PRODUCT | VERIFY THAT BUTTON SHOULD WORK WITH PRODUCT | 1. GO TO https://www.saucedemo.com/ 2. LOGIN TO PAGE 3. CLICK ON CHECKOUT ICON 4. VERIFY CHECKOUT BUTTON OPEN SUCCESSFULLY 5. VERIFY PRODUCT IS PRESENT IN CHECKOUT FIELD 6. CLICK ON CHECKOUT BUTTON 7. CLICK ON SECOND TIME CHECKOUT BUTTON 8. VERIFY SHOULD REDIRECT TO CHECKOUT YOUR INFORMATION PAGE | CHECKOUT BUTTON WORK PROPERLY WITH PRODUCTS. | DONE. |  | NO BUG | NA | NA
TS_10 | CHECKOUT SUCCESSFULLY | TC_10 | CHECKOUT WITH INFORMATION | VERIFY THAT ALL CHECKOUT INFORMATION, INCLUDING FIRST NAME, LAST NAME, AND ZIP CODE, IS WORKING CORRECTLY. | 1. GO TO https://www.saucedemo.com/ 2. LOGIN TO PAGE 3. CLICK ON CHECKOUT ICON 4. VERIFY CHECKOUT BUTTON OPEN SUCCESSFULLY 5. VERIFY PRODUCT IS PRESENT IN CHECKOUT FIELD 6. CLICK ON CHECKOUT BUTTON 7. CLICK ON SECOND TIME CHECKOUT BUTTON 8. VERIFY SHOULD REDIRECT TO CHECKOUT INFORMATION PAGE 9. FILL CORRECT INFORMATION INTO FIRSTNAME,LASTNAME AND ZIPCODE 10. VERIFY SHOULD REDIRECT TO CONFIRM ORDER PAGE | LAST NAME FIELD SHOULD BE ACCEPT INPUT AND CLICKABLE. | NOT LAST NAME FIELD IS SELECTABLE. | MAJOR | RE - TEST | NA | NOT WORKING LAST NAME FIELD FOR INPUT
TS_11 | RESET APP STATE SUCCESSFULLY | TC_11 | RESET ALL PRODUCT AS A DEFAULT | VERIFY THAT ALL PRODUCT SHOULD REMOVE FROM CART WITH RESET APP STATE | 1. GO TO https://www.saucedemo.com/ 2. LOGIN TO PAGE 3. CLICK ON CHECKOUT ICON 4. VERIFY CHECKOUT BUTTON OPEN SUCCESSFULLY 5. VERIFY PRODUCT IS PRESENT IN CHECKOUT FIELD 6. CLICK ON MENU BUTTON 7. CLICK ON RESET APP STATE BUTTON 8. VERIFY SHOULD ALL PRODUCT REMOVE FROM CART AND PRODUCT DISPLAY ADD TO CART | USER SHOULD RESET APP STATE WITH RESET APP STATE BUTTON SUCCESSFULLY. | BUTTON IS NOT WORK PROPERLY . | MAJOR | RE - TEST | NA | NOT RESET PRODUCT WITH RESET APP STATE MENU

## GLITCH_USER
TS_ID | TEST SCENARIOS | TC_ID | TEST CASES | DESCRIPTION | TEST STEPS | EXPECTED RESULT | ACTUAL RESULT | PRIORITY | STATUS | INPUT DATA | COMMENT
TS_01 | LOGIN SUCCESS | TC_01 | RIGHT ID AND RIGHT PASSWORD | VERIFY THAT WITH CORRECT USER ID & CORRECT PASSWORD USER SHOULD SUCCESSFULLY LOGIN (id : performance_glitch_user password : secret_sauce) | 1. GO TO https://www.saucedemo.com/ 2. CLICK ON FIELD NAME USERNAME 3. FILL CORRECT USERNAME 4. FILL CORRECT PASSWORD 5. CLICK ON LOGIN BUTTON 6. VERIFY THAT USER IS LOGGED IN | NO GLITCHES | GLITCH RAISED | MINOR | ON HOLD | USERNAME: glitch_user PASSWORD: sauce_secret | NA
TS_02 | OPEN PRODUCT | TC_02 | VERIFY THAT OPEN PRODUCT > THEN GO BACK THAN GLITCH | VERIFY THAT OPEN PRODUCT > THEN GO BACK THAN GLITCH | 1. GO TO https://www.saucedemo.com/ 2. LOGIN TO PAGE 3. OPEN PRODUCT 4. GO BACK | NO GLITCHES | GLITCH RAISED | MINOR | ON HOLD | NA | NA
TS_03 | BACK TO HOME | TC_03 | VERIFY THAT AFTER ORDER BACK TO HOME | VERIFY THAT AFTER ORDER BACK TO HOME SHOULD NOT GLITCH | 1. GO TO https://www.saucedemo.com/ 2. LOGIN TO PAGE 3. OPEN PRODUCT 4. CLICK ON CHECKOUT 5. VERIFY CHECKOUT IS OPEN SUCCESSFULLY 6. FILL THE INFORMATION TO ORDER 7. CLICK ON CHECKOUT 8. CLICK ON BACK TO HOME 9. VERIFY SHOULDN'T GLITCH IN BACK TO HOME | NO GLITCHES | GLITCH RAISED | MINOR | ON HOLD | NA | NA
TS_04 | PRODUCT ADD | TC_04 | VERIFY THAT PRODUCT ADD INTO CART | VERIFY THAT CHOOSE THE ANY PRODUCT > ADD INTO CART >VERIFY SHOULDN'T GLITCH | 1. GO TO https://www.saucedemo.com/ 2. LOGIN TO PAGE 3. CLICK ON PRODUCT ADD TO CART 4. VERIFY PRODUCT SHOULD ADD INTO CART WITHOUT GLITCH | NO GLITCHES | GLITCH RAISED |  | ON HOLD | NA | NA
TS_05 | PRODUCT FILTER | TC_05 | VERIFY THAT PRODUCT FILTERING | VERIFY THAT ALL PRODUCT SHOULD ARRANGE ACCORDING TO FILTER | 1. GO TO https://www.saucedemo.com/ 2. LOGIN TO PAGE 3. CLICK ON FILTER FIELD 4. VERIFY ALL PRODUCT SHOULD ARRANGE ACCORDING TO FILTER WITHOUT GLITCH | NO GLITCHES | GLITCH RAISED | MINOR | ON HOLD | NA | NA
TS_06 | PRODUCT RESET | TC_06 | VERIFY THAT PRODUCT RESET | VERIFY THAT ALL PRODUCT SHOULD RESET ACCORDING TO RESET APP STATE | 1. GO TO https://www.saucedemo.com/ 2. LOGIN TO PAGE 3. CLICK ON MENU BUTTON 4. CLICK ON RESET APP STATE 5. VERIFY ALL PRODUCT SHOULD RESET ACCORDING TO RESET APP STATE WITHOUT GLITCH | NO GLITCHES | GLITCH RAISED | MINOR | ON HOLD | NA | NA
TS_07 | ALL ITEAM | TC_07 | VERIFY THAT ALL PRODUCT SHOW WITH ALL ITEAM | VERIFY ALL APP SHOW WITH CLICK ON ALL ITEAM FIELD | 1. GO TO https://www.saucedemo.com/ 2. LOGIN TO PAGE 3. CLICK ON MENU BUTTON 4. CLICK ALL ITEAM 5. VERIFY ALL PRODUCT SHOULD SHOW ACCORDING TO ALL ITEAM WITHOUT GLITCH | NO GLITCHES | GLITCH RAISED | MINOR | ON HOLD | NA | NA
TS_08 | HOME PAGE | TC_08 | VERIFY REDIRECTION OF HOME PAGE | VERIFY ALL PAGE REDIRECT HOME PAGE WITH BACK BUTTON | 1. GO TO https://www.saucedemo.com/ 2. LOGIN TO PAGE 3. CLICK ON MENU BUTTON 4. CLICK ABOUT 5. CLICK ON BACK BUTTON 6. VERIFY HOME PAGE SHOULD SHOW ACCORDING TO BACK BUTTON WITHOUT GLITCH | NO GLITCHES | GLITCH RAISED | MINOR | ON HOLD | NA | NA
ALL FUNCTION IN THIS USER WORKING PROPERLY BUT SOME GLITHCES ARE RAISED

## ERROR_USER
TS_ID | TEST SCENARIOS | TC_ID | TEST CASES | DESCRIPTION | TEST STEPS | EXPECTED RESULT | ACTUAL RESULT | PRIORITY | STATUS | INPUT DATA | COMMENT
TS_01 | LOGIN SUCCESS | TC_01 | VERIFY THAT LOGIN SUCCESSFULLY(NO ERROR) | VERIFY THAT LOGIN SUCCESSFULLY (POP UP MESSAGE SHOWN) | 1. GO TO https://www.saucedemo.com (CHROME BROWSER) 2. LOGIN TO PAGE 3. POP UP MESSAGE SHOWN TO CHANGE PASSWORD | USER LOGIN SUCCESSFULLY | USER CAN LOGIN BUT POP UP MESSAGE SHOWN | MAJOR | NO BUG | USERNAME: error_user PASSWORD: secret_sauce | NA
TS_02 | ADD TO CART | TC_02 | ADD PRODUCT TO CARD | VERIFY THAT ALL PRODUCT SHOULD ADD TO CART SUCCESSFULLY | 1. GO TO https://www.saucedemo.com AND LOGIN 2. CLICK ON ANY PRODUCT ADD TO CART 3. VERIFY USER CAN ADD PRODUCT INTO CART | USER CAN ADD PRODUCT IN CART | UNABLE TO ADD ALL PRODUCTS IN CART | MAJOR | RE - TEST | NA | NA
TS_03 | REMOVE FROM CART | TC_03 | VERIFY REMOVE PRODUCT | VERIFY THAT ALL PRODUCT SHOULD REMOVE FROM CART SUCCESSFULLY | 1. GO TO https://www.saucedemo.com AND LOGIN 2. CLICK ON ANY PRODUCT ADD TO CART 3. VERIFY PRODUCT IS ADD INTO CART 4. CLICK ON THAT PRODUCT REMOVE BUTTON 5. VERIFY PRODUCT REMOVE FROM CART | USER CAN REMOVE PRODUCT FROM CART | USER CAN NOT REMOVE PRODUCT | MAJOR | RE - TEST | NA | NA
TS_04 | PRODUCT DETAILS | TC_04 | VERIFY THAT OPEN PRODUCT DETAILS | VERIFY THAT ALL PRODUCT DETAILS SHOULD OPEN SUCCESSFULLY | 1. GO TO https://www.saucedemo.com AND LOGIN 2. CLICK ON ANY PRODUCT NAME OR IMAGE 3. VERIFY PRODUCT DETAILS IS OPEN OR NOT 4. VERIFY PRODUCT DETAILS OPEN SUCCESSFULLY | OPEN PRODUCT DETAILS SUCCESSFULLY | DONE | MAJOR | NO BUG | NA | NA
TS_05 | SORT ITEMS | TC_05 | VERIFY THAT SORT ITEMS BUTTON WORKING PROPERLY | VERIFY THAT SORT ITEMS BUTTON WORKING PROPERLY (SEE COMMENT) | 1. GO TO https://www.saucedemo.com AND LOGIN (CHROME BROWSER) 2. CLICK ON ANY PRODUCT ADD TO CART 3. VERIFY PRODUCT IS ADD INTO CART 4. CLICK ON THAT PRODUCT REMOVE BUTTON 5. VERIFY PRODUCT REMOVE FROM CART | ITEM SORTING WORKING PROPERLY | NOT WORKING | MINOR | RE - TEST | NA | POP UP MESSAGE SHOWN FOR BROKEN SORTING
TS_06 | RESET APP STATE | TC_06 | VERIFY THAT RESET APP STATE WORKING | VERIFY THAT AFTER CLICK ON RESET ITEMS REMOVED FROM CART AND ALSO REMOVED FROM PRODUCT BAR | 1. GO TO https://www.saucedemo.com AND LOGIN 2. CLICK ON ANY PRODUCT ADD TO CART 3. VERIFY PRODUCT IS ADD INTO CART 4. CLICK ON RESET APP STATE BUTTON | ITEMS REMOVED FROM CART AFTER CLICK ON RESET | NOT WORKING | MAJOR | RE - TEST | NA | ITEM REMOVED FROM CART BUT NOT REMOVED FROM PRODUCT BAR
THIS WEBSITE CONTAIN ONLY ERROR FOR THE PRACTICE PURPOSE SO NO MORE TEST CASES ARE INVOLVED

## VISUAL_USER
TS_ID | TEST SCENARIOS | TC_ID | TEST CASES | DESCRIPTION | TEST STEPS | EXPECTED RESULT | ACTUAL RESULT | PRIORITY | BUG STATUS | INPUT DATA | COMMENT
TS_01 | CART POSITION | TC_01 | VERIFY CART POSITION | VERIFY THAT CART BUTTON IS AT RIGHT POSITION | 1. GO TO https://www.saucedemo.com 2. LOGIN INTO PAGE 3. CHECK THE POSITION OF CART | VERIFY THAT CART IS ON RIGHT POSITION AS PER THE REQUIREMENT | CART POSITION CHANGED | MINOR | RE - TEST | NA | NA
TS_02 | RESET APP STATE | TC_02 | VERIFY THAT RESET APP STATE WORKING | VERIFY THAT AFTER CLICK ON RESET ITEMS REMOVED FROM CART AND ALSO REMOVED FROM PRODUCT BAR | 1. GO TO https://www.saucedemo.com AND LOGIN 2. CLICK ON ANY PRODUCT ADD TO CART 3. VERIFY PRODUCT IS ADD INTO CART 4. CLICK ON RESET APP STATE BUTTON | IF USER CLICK ON RESET THAN RESET ALL FILTERS | RE TEST ALL FILTERS NOT WORKING PROPERLY | MAJOR | RE - TEST | NA | NA
TS_03 | SORT ITEMS | TC_03 | VERIFY THAT SORT ITEM WORKING | VERIFY THAT SORT ITEM WORKING | 1. GO TO https://www.saucedemo.com AND LOGIN 2. CLICK ON SORT BUTTON 3. SELECT ANY SORTING METHOD | CHECK THAT PRODUCT SORT BUTTON WORKING | PRODUCT SORTING NOT WORKING | MAJOR | RE - TEST | NA | HIGH TO LOW AND LOW TO HIGH SOORTING METHOD NOT WORKING
TS_04 | PRODUCT DETAIL | TC_04 | VERIFY PRODUCT DETAIL SAME AFTER OPEN DETAILS | VERIFY PRODUCT DETAIL SAME AFTER OPEN DETAILS | 1. GO TO https://www.saucedemo.com AND LOGIN 2. SEE ANY PRODUCT DETAILS AND NOTE IT 3. OPEN SAME PRODUCT SAME PRODUCT DETAILS | ANY PRODUCT DETAILS REMAIN SAME AFTER AR BEFORE OPENING | DETAILS CHANGED RANDOMLY | MAJOR | RE - TEST | NA | PRODUCT DETAIL CHANGED
TS_05 | ALL ITEMS BUTTON | TC_05 | VERIFY ALL ITEMS BUTTON WORKING PROPERLY | VERIFY ALL ITEMS BUTTON WORKING PROPERLY | 1. GO TO https://www.saucedemo.com AND LOGIN 2. CLICK ON THE OPTION BUTTON(3 LINE) 3. CLICK ON THE ALL ITEMS | ALL ITEMS BUTTON WORKING PROPERLY | ALL ITEMS BUTTON NOT WORKING PROPERLY | MINOR | RE - TEST | NA | ITEMS PRICE AND OTHER DETAILS CHANGED RANDOMLY WHEN CLICK ON ALL ITEMS
TS_06 | FIRST ITEM | TC_06 | VERIFY ALL DETAILS OF FIRST ITEM | VERIFY THAT ALL DETAILS ABOUT THAT ITEM REAMIN CONSTANT | 1. GO TO https://www.saucedemo.com AND LOGIN 2. CLICK ON FIRST PRODUCT 3. NOTICE THE CHANGED PHOTO OF ITEM AFTER OPEN DETAIL | ALL DETAILS REMAIN SAME | PRODUCT DETAIL CHANGED | MAJOR | RE - TEST | NA | PRODUCT BAR > DIFFERENT PHOTO OPEN PRODUCT > DIFFERENT PHOTO
TS_07 | CHECK OUT BUTTON POSITION | TC_07 | VERIFY THE POSITION OF CHECK OUT BUTTON | VERIFY THE POSITION OF CHECK OUT BUTTON | 1. GO TO https://www.saucedemo.com AND LOGIN 2. CLICK ON CART 3. SEE THE POSITION OF CHECK OUT BUTTON | CHECK OUT BUTTON POSITION AS PER THE REQUIREMENT | POSITION CHANGED | MINOR | RE - TEST | NA | NA
ALL VISUALS ARE CORRECT EXPECT THOSE 8 CASES